## Tracker Log
SL No. | MODULES | SUB-MODULES | TOTAL TC | COUNT PASS TC | COUNT FAIL TC | COUNT HOLD | COUNT LOGED IN JIRA | COUNT BUG FIXED | TESTER Name | START DATE | END DATE | BUG FIXED BY | STATUS | REMARKS | REFERENCE SHEET NAME | FILE HYPERLINK NAME | REVIEWED BY | REVIEWED DATE | Use Case Status
1 | Masters | Party --> Bank BRO | 55 | 42 | 13 |  | 13 | 13 | Shivam Singh | 2025-11-07 | 2026-01-23 | Pooja/Suraj Rana | Done |  |  | Bank_BRO | Sudhir kumar sinha |  | Updated
2 | Masters | Party --> CFS Master | 75 | 45 | 30 |  | 30 | 30 | Shivam Singh | 2025-11-14 | 2026-01-12 | Pooja/Suraj Rana | Done |  |  | CFS Master | Sudhir kumar sinha |  | Updated
3 | Masters | EDI Master --> Currency | 29 | 27 | 2 |  | 2 | 2 | Shivam Singh | 2025-11-22 | 2026-01-06 | Suraj Rana | Done |  |  | Currency | Sudhir kumar sinha |  | Updated
4 | Masters | EDI Master --> RITC | 29 | 19 | 10 |  | 10 | 10 | Shivam Singh | 2025-11-25 | 2026-02-02 | Suraj Rana | Done |  |  | RITC | Sudhir kumar sinha |  | Updated
5 | Masters | EDI Master --> Port | 21 | 14 | 7 |  | 7 |  | Shivam Singh | 2025-11-29 |  |  | Pending |  |  | Port | Sudhir kumar sinha
6 | Masters | EDI Master --> Loading & CHA Port | 0 | [5 empty] | Shivam Singh |  |  |  | Pending |  |  | Loading & CHA Port | Sudhir kumar sinha
7 | Masters | Regional Master --> Zone Master | 20 | 15 | 5 |  | 5 | 5 | Shivam Singh | 2025-12-01 | 2026-01-13 | Suraj Rana | Done |  |  | Zone Master | Sudhir kumar sinha |  | Updated
8 | Masters | Regional Master --> Country Master | 25 | 17 | 8 |  | 8 | 8 | Shivam Singh | 2025-12-01 | 2026-02-26 | Suraj Rana | Done |  |  | Country Master | Sudhir kumar sinha |  | Updated
9 | Masters | Regional Master --> Region Master | 23 | 18 | 5 |  | 5 | 5 | Shivam Singh | 2025-12-02 | 2026-02-02 | Suraj Rana | Done |  |  | Region Master | Sudhir kumar sinha |  | Updated
10 | Masters | Regional Master --> FF Port Master | 26 | 17 | 9 |  | 9 | 9 | Shivam Singh | 2025-12-03 | 2026-03-05 | Suraj Rana | Done |  |  | FF Port Master | Sudhir kumar sinha |  | Updated
11 | Masters | Regional Master --> Action Master | 19 | 11 | 8 |  | 8 |  | Shivam Singh | 2025-12-04 |  |  | Pending |  |  | Action Master | Sudhir kumar sinha
12 | Masters | Regional Master --> Period Master | 16 | 10 | 6 |  | 6 |  | Shivam Singh | 2025-12-09 |  |  | Pending |  |  | Period Master | Sudhir kumar sinha
13 | Masters | Regional Master --> Cost Center Master | 18 | 12 | 6 |  | 6 | 6 | Shivam Singh | 2025-12-09 | 2026-02-26 | Suraj Rana | Done |  |  | Cost Center Master | Sudhir kumar sinha |  | Updated
14 | Masters | Shipment info --> IMO Master | 18 | 12 | 6 |  | 6 | 6 | Shivam Singh | 2025-12-10 | 2026-02-26 | Suraj Rana | Done |  |  | IMO Master | Sudhir kumar sinha |  | Updated
15 | Masters | Shipment info --> Unit Master | 15 | 9 | 6 |  | 6 | 6 | Shivam Singh | 2025-12-10 | 2026-02-02 | Suraj Rana | Done |  |  | Unit Master | Sudhir kumar sinha |  | Updated
16 | Masters | Shipment info --> CHA Service | 23 | 17 | 6 |  | 6 | 6 | Shivam Singh | 2025-12-11 | 2026-02-10 | Suraj Rana | Done |  |  | CHA Service | Sudhir kumar sinha |  | Updated
17 | Masters | Charge Master - Pricing | 60 | 42 | 13 | 5 | 13 |  | Shivam Singh | 2025-12-12 |  |  | Pending |  |  | Pricing | Sudhir kumar sinha
18 | Masters | Charge Master - Cost/Revenue Master | 59 | 33 | 20 | 6 | 20 |  | Shivam Singh | 2025-12-16 |  |  | Pending |  |  | Sea Charge Master | Sudhir kumar sinha
19 | Masters | Misc Master - Segment Master | 30 | 23 | 7 |  | 7 | 7 | Shivam Singh | 2025-12-20 | 2026-02-26 | Suraj Rana | Done |  |  | Segment Master | Sudhir kumar sinha |  | Updated
20 | Masters | Misc Master - Trigger Master | 25 | 17 | 8 |  | 8 | 8 | Shivam Singh | 2025-12-20 | 2026-02-26 | Suraj Rana | Done |  |  | Trigger Master | Sudhir kumar sinha |  | Updated
21 | Masters | Misc Master - Pricniple Line HBL Master | 15 | 10 | 5 |  | 5 | 5 | Shivam Singh | 2025-12-22 | 2026-03-09 | Suraj Rana | Done |  |  | Principle Line HBL Master | Sudhir kumar sinha |  | Updated
22 | Masters | Misc Master - Project Type Master | 19 | 13 | 6 |  | 6 | 6 | Shivam Singh | 2025-12-23 | 2026-03-09 | Suraj Rana | Done |  |  | Project Type Master | Sudhir kumar sinha |  | Updated
23 | Masters | Misc Master - Notes, Terms & Conditions | 23 | 17 | 6 |  | 6 | 6 | Shivam Singh | 2025-12-23 | 2026-03-09 | Suraj Rana | Done |  |  | Notes Master | Sudhir kumar sinha |  | Updated
24 | Masters | Vessel Info - Vessel | 19 | 13 | 6 |  | 6 | 6 | Shivam Singh | 2025-12-24 | 2026-03-09 | Suraj Rana | Done |  |  | Vessel | Sudhir kumar sinha |  | Created / Updated
25 | Masters | Vessel Info - Schedule | 76 | 49 | 27 |  | 18 |  | Shivam Singh | 2025-12-26 |  |  | Pending |  |  | Schedule | Sudhir kumar sinha
26 | Masters | Shipment Status | 20 | 12 | 8 |  | 8 |  | Shivam Singh | 2026-01-01 |  |  | Pending |  |  | Shipment Status | Sudhir kumar sinha
27 | Masters | Destuffing | 16 | 11 | 5 |  | 5 |  | Shivam Singh | 2026-01-05 |  |  | Pending |  |  | Destuffing | Sudhir kumar sinha
28 | Masters | Document | 15 | 14 | 1 |  | 1 |  | Shivam Singh | 2026-01-05 |  |  | Pending |  |  | Document | Sudhir kumar sinha
29 | Masters | Container | 21 | 10 | 11 |  | 11 |  | Shivam Singh | 2026-01-06 |  |  | Pending |  |  | Container | Sudhir kumar sinha
30 | Masters | Stuffing Master | 16 | 7 | 9 |  | 9 | 9 | Shivam Singh | 2026-01-08 | 2026-02-10 |  | Done |  |  | Stuffing Master | Sudhir kumar sinha |  | Created / Updated
31 | Masters | Daily Currency Rate | 13 | 10 | 3 |  | 3 |  | Shivam Singh | 2026-01-07 |  |  | Pending |  |  | Daily Currency Rate | Sudhir kumar sinha
32 | Masters | Container Yard Master | 18 | 11 | 7 |  | 7 |  | Shivam Singh | 2026-01-08 |  |  | Pending |  |  | Container Yard Master | Sudhir kumar sinha
33 | Masters | Create Branch | 38 | 15 | 20 | 3 | 7 |  | Shivam Singh | 2026-01-14 |  |  | Pending |  |  | Create Branch | Sudhir kumar sinha
34 | Masters | Shipment Plan Master | 14 | 6 | 8 |  | 8 |  | Shivam Singh | 2026-02-27 |  |  | Pending |  |  | Shipment Plan Master | Sudhir kumar sinha
35 | Masters | EDI Master --> CHA Port Master | 15 | [5 empty] | Shivam Singh | 2026-01-30 |  |  | Pending |  |  | CHA Port Master | Sudhir kumar sinha
36 | Masters | EDI Master --> Transporter Master | 15 | [5 empty] | Shivam Singh | 2026-01-31 |  |  | Pending |  |  | Transporter Master | Sudhir kumar sinha
37 | Masters | EDI Master --> Drawback Schedule | 25 | [5 empty] | Shivam Singh | 2026-02-02 |  |  | Pending |  |  | Drawback Schedule | Sudhir kumar sinha
38 | Masters | EDI Master --> Country | 14 | [5 empty] | Shivam Singh | 2026-02-04 |  |  | Pending |  |  | EDI-Country | Sudhir kumar sinha
39 | Masters | EDI Master --> Licence Master New | 5 | [5 empty] | Shivam Singh | 2026-02-04 |  |  | Pending |  |  | Licence Master New | Sudhir kumar sinha
40 | Masters | EDI Master --> eSanchit Code | 17 | [5 empty] | Shivam Singh | 2026-02-05 |  |  | Pending |  |  | eSanchit Code | Sudhir kumar sinha
41 | Masters | EDI Master --> CESS Schedule Master | 25 | [5 empty] | Shivam Singh | 2026-02-06 |  |  | Pending |  |  | CESS Schedule Master | Sudhir kumar sinha
42 | Masters | EDI Master --> Rodtep Master | 19 | [5 empty] | Shivam Singh | 2026-02-07 |  |  | Pending |  |  | Rodtep Master | Sudhir kumar sinha
43 | Masters | EDI Master --> Vehicle Owner Master | 20 | [5 empty] | Shivam Singh | 2026-02-09 |  |  | Pending |  |  | Vehicle Owner Master | Sudhir kumar sinha
44 | Masters | EDI Master --> Item Template Master | 26 | [5 empty] | Shivam Singh | 2026-02-10 |  |  | Pending |  |  | Item Template Master | Sudhir kumar sinha
45 | Masters | EDI Master --> ROSL DBK | 26 | [5 empty] | Shivam Singh | 2026-02-11 |  |  | Pending |  |  | ROSL DBK | Sudhir kumar sinha
46 | Masters | EDI Master --> Licence Master | 29 | [5 empty] | Shivam Singh | 2026-02-13 |  |  | Pending |  |  | Licence Master | Sudhir kumar sinha
47 | Operation | Shipment Registration | 115 | [5 empty] | Shivam Singh | 2026-01-19 |  |  | Pending |  |  | Shipment Reg-Shipment | Sudhir kumar sinha
48 | Accounts | Master -> Ledger Account | 94 | [5 empty] | Shivam Singh | 2026-02-16 |  |  | Pending |  |  | Ledger Account | Sudhir kumar sinha
49 | Accounts | Master -> GST Charges | 45 | [5 empty] | Shivam Singh | 2026-02-25 |  |  | Pending |  |  | GST Charges | Sudhir kumar sinha
50 | Operation | Shipment Plan -> Shipment Plan | 11 | 7 | 4 |  | 4 |  | Shivam Singh | 2026-02-27 |  |  | Pending |  |  | Shipment Plan | Sudhir kumar sinha
51 | Accounts | Master -> TDS Schedule | 12 | [5 empty] | Shivam Singh | 2026-03-03 |  |  | Pending |  |  | TDS Schedule | Sudhir kumar sinha
52 | Accounts | Master -> Charge Rules | 12 | [5 empty] | Shivam Singh | 2026-03-03 |  |  | Pending |  |  | Charge Rules | Sudhir kumar sinha
53 | Accounts | Master -> Item Master | 21 | [5 empty] | Shivam Singh | 2026-03-06 |  |  | Pending |  |  | Item Master | Sudhir kumar sinha
54 | Accounts | Master -> Division Mapping | 4 | [5 empty] | Shivam Singh | 2026-03-07 |  |  | Pending |  |  | Division Mapping | Sudhir kumar sinha
55 | Accounts | Master -> TDS Party | 29 | [5 empty] | Shivam Singh | 2026-03-07 |  |  | Pending |  |  | TDS Party | Sudhir kumar sinha
56 | Accounts | Master -> SAC Master | 18 | [5 empty] | Shivam Singh | 2026-03-10 |  |  | Pending |  |  | SAC Master | Sudhir kumar sinha
57 | Accounts | Master -> Depreciation Rates Master | 13 | [5 empty] | Shivam Singh | 2026-03-11 |  |  | Pending |  |  | Depreciation Rates Master | Sudhir kumar sinha
58 | Accounts | Master -> Merge Accounts | 9 | [5 empty] | Shivam Singh | 2026-03-12 |  |  | Pending |  |  | Merge Accounts | Sudhir kumar sinha
59 | Accounts | Voucher -> Receipt Voucher | 18 | [5 empty] | Shivam Singh | 2026-03-12 |  |  | Pending |  |  | Receipt Voucher | Sudhir kumar sinha

## Extra Id
Extra Bug Id - Not Recorded in Test Cases
BA-482
BA-256
BA-443
BA-656