## ICaffe_Tracker
SL No. | MODULES | SUB-MODULES | TOTAL TC | COUNT PASS TC | COUNT FAIL TC | COUNT HOLD | COUNT LOGED IN JIRA | COUNT BUG FIXED | TESTER Name | START DATE | END DATE | BUG FIXED BY | STATUS | REMARKS | REFERENCE SHEET NAME | FILE HYPERLINK NAME | REVIEWED BY | REVIEWED DATE
1 | Master | Party->Exporter Tab As- 1. Shipper | 68 | 53 | 15 |  | 15 | 15 | Akash varun | 2025-08-04 | 2025-12-08 | Pooja | Completed | The IEC number is classified as Government and has been accepted as a duplicate data entry in the master record. | Shipper | Go to Shipper | Sudhir kumar sinha | 2026-01-05
2 | Master | Party->Exporter Tab As- 2. Other Details | 10 | 9 | 1 |  | 1 | 1 | Akash varun | 2025-08-08 | 2025-08-13 | Pooja | Completed | The IEC number is classified as Government and has been accepted as a duplicate data entry in the master record. | Shipper_OtherDetails | Go to Shipper_OtherDetails | Sudhir kumar sinha | 2026-01-05
3 | Master | Party->Exporter Tab As- 3. Contact Details | 30 | 24 | 6 |  | 6 | 6 | Akash varun | 2025-08-11 | 2025-09-08 | Pooja | Completed | The IEC number is classified as Government and has been accepted as a duplicate data entry in the master record. | Shipper_ContactDeteails | Go to Shipper_ContactDeteails | Sudhir kumar sinha | 2026-01-05
4 | Master | Party->Exporter Tab As- 1. Shipper | 2 |  |  | 2 | 2 |  | Akash varun | 2025-08-04 |  | Pooja | HOLD | 2 (Pending: Page not responsive; Excel Upload button is hidden (discussed with dev team)) | Shipper | Go to Shipper | Sudhir kumar sinha | 2026-01-05
5 | Master | Party->Consignee | 44 | 36 | 8 |  | 8 | 8 | Akash varun | 2025-08-13 | 2025-09-11 | Pooja | Completed | For foreign countries, the PIN code has been accepted as a string (alphanumeric) value. | Consignee | Go to Consignee | Sudhir kumar sinha | 2026-01-05
6 | Master | Party->Sub Agent | 56 | 51 | 5 |  | 5 | 5 | Akash varun | 2025-08-20 | 2025-09-10 | Pooja | Completed | BA-429 (This Jira bug ID is marked as duplicate because the same issue occurs). | Sub_Agent | Go to Sub_Agent | Sudhir kumar sinha | 2026-01-07
7 | Master | Party->Sub Agent->Contact Details | 38 | 28 | 10 |  | 10 | 10 | Akash varun | 2025-08-30 | 2025-09-10 | Pooja | Completed |  | SubAgent_ContactDetails | Go to SubAgent_ContactDetails | Sudhir kumar sinha | 2026-01-07
8 | Master | Party->Overseas Agent | 51 | 38 | 13 |  | 13 | 13 | Akash varun | 2025-09-02 | 2025-09-23 | Pooja | Completed |  | Overseas_Agent | Go to OverSeas_Agent | Sudhir kumar sinha | 2026-01-07
9 | Master | Party->Overseas Agent->Contact Details | 36 | 28 | 8 |  | 8 | 8 | Akash varun | 05-09-2025 | 2025-09-10 | Pooja | Completed |  | Overseas_Agent OverSeasAgent_ContactDetails | Go to OverSeasAgent_ContactDetails | Sudhir kumar sinha | 2026-01-07
10 | Master | Party->Overseas Agent | 2 |  |  | 2 | 2 |  | Akash varun | 2025-09-02 |  | Pooja | HOLD | 2 (Pending: Page not responsive) | OverSeasAgent_ContactDetails | Go to OverSeas_Agent | Sudhir kumar sinha | 2026-01-07
11 | Master | Party->ShipLine | 64 | 50 | 14 |  | 14 | 14 | Akash varun | 2025-09-06 | 2025-09-24 | Pooja | Completed | BA-429 (This Jira bug ID is marked as duplicate because the same issue occurs). | ShipLine | Go to ShipLine | Sudhir kumar sinha | 2026-01-08
12 | Master | Party->ShipLine->Contact Details | 36 | 27 | 9 |  | 9 | 9 | Akash varun | 2025-09-11 | 2025-09-24 | Pooja | Completed |  | ShipLine_ContactDetails | Go to ShipLine_ContactDetails | Sudhir kumar sinha | 2026-01-08
13 | Master | Party->IATA Agent | 41 | 37 | 4 |  | 4 | 4 | Akash varun | 2025-09-12 | 2025-09-24 | Pooja | Completed | BA-429 (this bug ID is used because the same issue occurs in Sub Agent and Shipline). | IATA_Agent | Go to IATA_Agent | Sudhir kumar sinha | 2026-01-08
14 | Master | Party->IATA Agent-> Contact Details | 34 | 26 | 8 |  | 8 | 8 | Akash varun | 2025-09-15 | 2025-09-24 | Pooja | Completed |  | IATAAgent_ContactDetails | Go to IATAAgent_ContactDetails | Sudhir kumar sinha | 2026-01-08
15 | Master | Party->Vendor Master | 75 | 65 | 10 |  | 10 | 7 | Akash varun | 2025-09-22 |  | Pooja | Pending |  | Vendor_Master | Go to Vendor_Master | Sudhir kumar sinha
16 | Operation | Overseas Agent (Inward RCM) Tab As- 1. Over Seas Invoice Inward (Reverse Charge 2. Search | 124 | 102 | 22 |  | 22 | 1 | Akash varun | 2025-09-29 |  |  | Pending | (this bug ID is used because the same issue occurs - 74) | Overseas Agent (Inward RCM) | Go to OverseasAgent_InwardRCM | Sudhir kumar sinha
17 | Operation | GST Invoice->Service-> Service Invoice> | 297 | 246 | 51 |  | 51 | 0 | Akash varun | 2025-10-11 |  |  | Pending |  | Service Invoice | Go to ServiceInvoice | Sudhir kumar sinha
18 | Operation | GST Invoice->Service-> Search | 70 | 57 | 13 |  | 13 | 0 | Akash varun | 2025-11-27 |  |  | Pending |  | ServiceInvoice_Search | Go to ServiceInvoice_Search | Sudhir kumar sinha
19 | Operation | GST Invoice->Service->Print | 47 | 26 | 21 |  | 21 | 0 | Akash varun | 2025-12-15 |  |  | Pending | (this bug ID is used because the same issue occurs. - 345,334,286) | ServiceInvoice_Print | Go to ServiceInvoice_Print | Sudhir kumar sinha
20 | Operation | GST Invoice->Service->Print | 2 |  |  | 2 |  | 0 | Akash varun | 2025-12-15 |  |  | Pending |  | ServiceInvoice_Print | Go to ServiceInvoice_Print | Sudhir kumar sinha
21 | Operation | GST Invoice->Reimbursable->Reimbursable Invoice | 144 | 111 | 33 |  | 33 | 0 | Akash varun | 2025-12-24 |  |  | Pending |  | Reimbursable_Invoice | Go to Reimbursable_Invoice | Sudhir kumar sinha
22 | Operation | GST Invoice->Reimbursable->Search | 70 | 56 | 14 |  | 14 | 0 | Akash varun | 2026-01-16 |  |  | Pending | (this bug ID is used because the same issue occurs. - 255) | ReimbursableInvoice_Search | Go to ReimbursableInvoice_Search | Sudhir kumar sinha
23 | Operation | GST Invoice->Reimbursable->Print | 48 | 26 | 22 |  | 22 | 0 | Akash varun | 2026-01-17 |  |  | Pending | (this bug ID is used because the same issue occurs. - 512,566,575) | ReimbursableInvoice_Print | Go to ReimbursableInvoice_Print | Sudhir kumar sinha
24 | Operation | GST Invoice->Transport | 111 | 90 | 21 |  | 21 | 0 | Akash varun | 2026-01-19 |  |  | Pending | (this bug ID is used because the same issue occurs. - 423,421) | Transport_Invoice | Go to Transport_Invoice | Sudhir kumar sinha
25 | Operation | GST Invoice->Transport->Search | 69 | 55 | 14 |  | 14 | 0 | Akash varun | 2026-02-07 |  |  | Pending |  | TransportInvoice_Search | Go to TransportInvoice_Search | Sudhir kumar sinha
26 | Operation | GST Invoice->Transport->Print | 49 | 28 | 21 |  | 21 | 0 | Akash varun | 2026-02-09 |  |  | Pending | (this bug ID is used because the same issue occurs. - 630,632) | TransportInvoice_Print | Go to TransportInvoice_Print | Sudhir kumar sinha
27 | Operation | GST Invoice->Transport->Print | 2 |  |  | 2 |  |  | Akash varun | 2026-02-09 |  |  | Pending |  | TransportInvoice_Print | Go to TransportInvoice_Print | Sudhir kumar sinha
28 | Operation | GST Invoice->Other Invoice | 205 | 161 | 44 |  | 44 | 0 | Akash varun | 2026-02-09 |  |  | Pending |  | Other_Invoice | Go to Other_Invoice | Sudhir kumar sinha
29 | Operation | GST Invoice->Other Invoice>Search | 51 | 45 | 6 |  | 6 | 0 | Akash varun | 2026-02-13 |  |  | Working |  | OtherInvoice_Search | Go to OtherInvoice_Search | Sudhir kumar sinha